## Timeline NHMAP
Natural Hazard Mitigation Plan Update Schedule
| June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February
| WK 0 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25 | WK 26 | WK 27 | WK 28 | WK 29 | WK 30 | WK 31 | WK 32 | WK 33 | WK 34 | WK 35 | WK 36
Overview of Tasks and Timeline
Objective 1 - Pre-Disaster Mitigation Local Plan Update Support
1.1 Check in call with client
1.2 Pre-project planning meeting (March '15)
Objective 2 - Finalize Project Work Plan | bar: June WK 1 to July WK 7
2.1 Identify Steering Committee Members | bar: June WK 2 to June WK 3
2.2 Project IGA and SOW examples obtained and reviewed | bar: June WK 1
2.3 Project IGA draft development | bar: July WK 4 to July WK 5
2.4 Project SOW draft development | bar: July WK 4 to July WK 5
2.5 Project IGA and SOW reviewed and approved | bar: July WK 4 to July WK 6
2.6 Kickoff Mtg. w/ local committee | bar: August WK 9
Objective 3 - Distribute Planning Resources | bar: July WK 7
3.1 Distribute planning tools | bar: July WK 7
3.2 Project webpage created | bar: July WK 7
Objective 4 - Update Community Profile | bar: July WK 5 to September WK 14
4.1 Update data for community profile | bar: July WK 4 to August WK 9
4.2 Complete "Goal 7 Crosswalk" | bar: August WK 11 to September WK 14
Objective 5 - Update Natural Hazard Identification and Risk Assessment | bar: July WK 5 to November WK 22
5.1 Gather and update hazard information | bar: July WK 5 to September WK 17
5.2 Coordinate with agency partners | bar: August WK 9 to August WK 12
5.3 Update vulnerability assessment | bar: August WK 11 to September WK 17
5.4 Risk Assessment Update Meeting | bar: September WK 16 to October WK 20
Objective 6 - Update Action Items and Implementation | bar: July WK 7 to November WK 22
6.1 Document completed action items from 2011 plan | bar: July WK 7 to August WK 11
6.2 Action Items Meeting | bar: October WK 18 to October WK 20
6.3 Update Action Items (Section 4) | bar: October WK 21 to November WK 22
6.4 Action Items Memo Change Update (Appendix A) | bar: October WK 21 to November WK 22
Objective 7 - Public Outreach | bar: June WK 2 to October WK 19
7.1 Coordinate public outreach and engagement actions with neighboring jurisdictions | bar: June WK 2 to October WK 18
7.2 Attend a public outreach events hosted by other jurisdictions | bar: June WK 2 to October WK 18
7.3 Create online survey for public engagement | bar: July WK 7 to September WK 17
7.4 Participate in public events to facilitate community engagement | bar: July WK 4 to September WK 17
7.5 Incorporate public comments into mitigation action items | bar: October WK 18 to October WK 19
7.6 Update Public Process (Appendic C) | bar: October WK 18 to October WK 19
Objective 8 - Draft Plan Prep and Review | bar: November WK 22 to December WK 29
8.1 Update Additional Maps and Accronyms Appendices | bar: November WK 22 to November WK 23
8.2 Complete final edits and draft preparation | bar: November WK 24
8.3 County and Cities review draft | bar: November WK 24
8.4 Submit draft to State for submittal to FEMA for preliminary review | November WK 25: 1 month FEMA review
8.5 Final draft creation | bar: December WK 29
Objective 9 - Final Plan Review and Adoption | bar: December WK 30 to February WK 36
9.1 County Plan Adoption | January WK 31: 3 weeks
9.2 Submit final draft to State for submittal and approval by FEMA | January WK 33: 1 month FEMA review

## Sheet3
South Coast Tentative Natural Hazard Mitigation Plan Update Schedule
| June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November
| WK 0 | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13 | WK 14 | WK 15 | WK 16 | WK 17 | WK 18 | WK 19 | WK 20 | WK 21 | WK 22 | WK 23 | WK 24 | WK 25
Overview of Tasks and Timeline
Task 1 - Pre-Disaster Mitigation Local Plan Update Support
Check in call with client
Task 2 - Finalize Project Work Plan | bar: June WK 1 to July WK 6
Work Plan Refinement | bar: June WK 1 to July WK 5
Schedule Refinement | bar: June WK 1 to July WK 5
Kickoff Mtg. w/ local committee | bar: June WK 3 to July WK 6
Task 3 - Identify and Compile Best Available Hazard Data | bar: June WK 1 to September WK 13
Identify new data sources | bar: June WK 1 to September WK 13
Coordinate with agency partners | bar: July WK 5 to August WK 8
List of best available data | bar: July WK 7 to August WK 8
Update hazard vulnerability assessment | bar: July WK 7 to August WK 10
Risk/Vulnerability Assessment Mtg. | bar: July WK 7 to August WK 11
Task 4 - Distribute Planning Resources | bar: July WK 5 to November WK 25
Distribute planning tools | bar: July WK 5 to July WK 6; November WK 25
Webpage updates | bar: July WK 5 to November WK 24
Task 5 - Update Community Profile and Existing Plans and policies | bar: June WK 2 to October WK 18
Research new data for community profile | bar: June WK 2 to August WK 11
Review existing plans and policies | bar: July WK 5 to September WK 12
Complete "Goal 7 Crosswalk" | bar: August WK 8 to September WK 12
Risk/Vulnerability Assessment Mtg. | bar: July WK 7 to August WK 11
Mitigation Strategy Mtg. | bar: August WK 10 to September WK 14
Completed profile and policy sections | bar: August WK 10 to October WK 18
Task 6 - City Specific Addenda Review and Update | bar: July WK 4 to November WK 24
Update hazard vulnerability assessment | bar: July WK 4 to October WK 18
Review and update mitigation strategy | bar: September WK 12 to October WK 18
City Addenda Update Mtgs. | bar: September WK 13 to October WK 18
Task 7 - Draft Plan Prep and Review | bar: September WK 12 to November WK 24
Complete draft NHMP for review | bar: September WK 12 to November WK 21
Public/OEM Comment Period | October WK 19: ~2 weeks
FEMA Review | November WK 21: 45 Day Review
Task 8 - Final Plan Review and Adoption | bar: November WK 25
Address any FEMA comments | bar: November WK 25
Local Adoption
Final FEMA Approval